MASTER INTEGRATION PLAN: CLI Agent Features into HelixCode

Document Version: 1.0
Date: 2025-01-20
Status: Draft for Review
Classification: Internal Engineering
Author: Integration Architecture Team

Section 1: EXECUTIVE SUMMARY

1.1 Vision Statement

HelixCode will become the unified, enterprise-grade AI-native code intelligence platform by systematically incorporating the best-of-breed capabilities from 10 leading CLI agent implementations (Claude Code, Aider, Cline, Codex, Plandex, Forge, Kilo Code, OpenCode, Gemini CLI, Amazon Q). This integration transforms HelixCode from a modular architecture into a cohesive “super-agent” capable of autonomous planning, sandboxed execution, multi-model orchestration, and enterprise-scale context management – all while maintaining the Go-based performance, Actor Model concurrency, and PostgreSQL/Redis persistence that define HelixCode’s core identity.

The vision is not to bolt features onto HelixCode, but to deeply integrate each capability into the existing architectural patterns: Cobra commands become slash commands, Gin handlers become MCP endpoints, Actor agents become specialized sub-agents, and the Tree-sitter code map becomes the foundation for context compaction and fuzzy matching.

1.2 Scope and Boundaries

IN SCOPE

- 4 missing submodules: HelixAgent, HelixLLM, HelixMemory, HelixSpecifier (addition via SSH)

- 3 uninitialized submodules: LLMsVerifier, HelixQA, Challenges, Containers (initialization and wiring)

- 20+ major feature domains across 10 CLI agent sources (see Feature Inventory below)

- Build system unification: Go 1.26 workspace across all submodules

- Configuration unification: Single Viper config tree with environment overlays

- Database schema evolution: PostgreSQL migrations for tool persistence, sessions, transcripts

- Redis data structures: Context windows, caches, session state

- API surface expansion: OpenAPI 3.0 spec updates for new endpoints

- Testing integration: 100% coverage mandate with HelixQA challenge sessions

OUT OF SCOPE (for this plan)

- Custom model training or fine-tuning (inference only)

- Mobile application development (CLI and desktop UI only)

- Third-party marketplace / plugin store (plugin system architecture only, no store)

- Billing/subscription engine (authentication only, billing deferred)

- Non-code LLM use cases (creative writing, general chat – code-focused only)

BOUNDARIES

- HelixCode remains the PRIMARY repository; HelixAgent is integrated as a submodule, not as a monorepo parent

- All LLM communication flows through the HelixCode gateway (no submodule direct provider access)

- Sandboxed execution is containerized (Docker/Podman) – no native OS process spawning without sandbox

- PostgreSQL is the single source of truth; Redis is ephemeral/cache only

1.3 Success Criteria

| # | Criterion | Measurement | Target |
| --- | --- | --- | --- |
| 1 | All 4 missing submodules added and building | git submodule status + go build ./... | 100% clean |
| 2 | All 3 uninitialized submodules active | Submodule status + CI pipeline | All initialized |
| 3 | Feature parity with Claude Code | Feature checklist (see Appendix A) | 95%+ coverage |
| 4 | Aider dual-model architecture | Integration test with architect/editor | Passing |
| 5 | MCP lifecycle complete | MCP test suite (4 transports + OAuth) | All passing |
| 6 | Context compaction operational | 1M+ token context handling | <2s compaction |
| 7 | Sandboxed shell execution | Security audit + functional test | No escapes |
| 8 | Plan/Act mode separation | User acceptance test | Seamless switching |
| 9 | 100% test coverage | go test -cover | >= 100% (all new code) |
| 10 | HelixQA challenge sessions | Challenge completion rate | >90% pass |
| 11 | OpenTelemetry observability | Trace coverage | All major flows traced |
| 12 | Performance baseline | p95 latency for key operations | <500ms edit, <2s plan |
| 13 | Theme system operational | UI rendering test | 6 platform themes render |
| 14 | Subagent delegation | Multi-agent workflow test | 3+ agents cooperate |
| 15 | LSP integration | Diagnostics feedback loop | <1s roundtrip |

Section 2: PHASES OVERVIEW

Phase 0: Foundation – Submodule Integration & Build System Fix

| Attribute | Detail |
| --- | --- |
| Phase Goal | Establish the complete repository structure with all 11 submodules (7 existing + 4 missing) properly linked, initialized, and building under a unified Go workspace. Fix SSH submodule resolution and build chain. |
| Entry Criteria | - Access to all repositories via SSH keys configured- Go 1.26 installed and verified- Current HelixCode builds successfully (baseline)- Submodule access rights confirmed for all 11 repos |
| Exit Criteria | - git submodule status shows all 11 submodules at expected commits- go work init + go work use produces clean workspace- go build ./... from HelixCode root succeeds- All submodule go.mod modules resolve without replace directives (or with approved ones)- CI pipeline passes on all platforms (Linux, macOS, Windows) |
| Duration Estimate | 5-7 calendar days |
| Risk Level | HIGH – SSH submodule topology is unusual (HelixCode is child of HelixAgent); circular dependency risk exists |
| Rollback Strategy | - Pre-phase git tag pre-phase0-baseline on HelixCode- Document original .gitmodules before modification- Keep backup branch backup/pre-submodule-merge- If build fails, revert .gitmodules and go.work |

Phase 1: Core Infrastructure – LLM Gateway, Memory, Spec Engine

| Attribute | Detail |
| --- | --- |
| Phase Goal | Build the three foundational services that all subsequent features depend on: a unified LLM gateway (incorporating OpenCode’s 75+ providers and multi-provider backend), a persistent memory/retrieval system (HelixMemory), and a specification engine (HelixSpecifier) for task decomposition and planning. |
| Entry Criteria | - Phase 0 exit criteria met- HelixLLM submodule builds independently- HelixMemory PostgreSQL schema designed- HelixSpecifier module interfaces defined |
| Exit Criteria | - LLM gateway routes to >= 5 providers with provider-specific config- Memory system persists and retrieves conversation context with embedding search- Spec engine decomposes a user prompt into actionable subtasks- All three systems have >= 90% unit test coverage- OpenAPI spec updated with /api/v1/llm, /api/v1/memory, /api/v1/spec endpoints- Redis connection pools configured for context caching |
| Duration Estimate | 14-18 calendar days |
| Risk Level | HIGH – LLM provider API drift; embedding model compatibility; spec engine accuracy |
| Rollback Strategy | - Feature flags for each service (--enable-llm-gateway, --enable-memory, --enable-spec)- Database migrations are reversible (down migrations tested)- Old provider factory remains accessible via LEGACY_PROVIDER_FACTORY=1 |

Phase 2: CLI Agent Foundation – Tool Framework, Context Management, Edit System

| Attribute | Detail |
| --- | --- |
| Phase Goal | Implement the core agent primitives: a pluggable tool framework (inspired by Claude Code’s tool system), context management with auto-compaction (Codex + Plandex), and a smart file editing system (Aider’s 4-layer fuzzy matching + Claude Code’s no-flicker rendering). |
| Entry Criteria | - Phase 1 exit criteria met- Tool interface contracts defined- Context window size limits configured per provider- File watcher / Tree-sitter integration tested |
| Exit Criteria | - Tool framework supports >= 10 tool types with registration/discovery- Context auto-compaction reduces 2M tokens to provider limit with <5% semantic loss- Smart file edit applies changes with >= 99% accuracy on test corpus- Fuzzy matching resolves file references with >= 95% success- No-flicker rendering tested on 6 UI platforms- Session transcript persistence to PostgreSQL |
| Duration Estimate | 18-22 calendar days |
| Risk Level | MEDIUM-HIGH – Context compaction quality is hard to validate; file edit accuracy depends on Tree-sitter coverage |
| Rollback Strategy | - AUTO_COMPACTION=off config flag- Legacy edit system preserved in pkg/edit/legacy- Context size can be manually capped |

Phase 3: Power Features – Plan Mode, Sandboxing, MCP, Permissions

| Attribute | Detail |
| --- | --- |
| Phase Goal | Deliver the differentiating agent capabilities: Plan/Act dual mode (Cline, Gemini CLI, Claude Code), sandboxed shell execution (Claude Code, Codex), full MCP lifecycle with OAuth (Claude Code), permission rule system with 5 modes + wildcards (Claude Code), background task system, and hook-based extensibility. |
| Entry Criteria | - Phase 2 exit criteria met- Container runtime available (Docker/Podman)- MCP spec 2024-11-05 compliance target set- Permission policy schema designed |
| Exit Criteria | - Plan mode generates actionable plans with user approval checkpoints- Sandboxed shell executes commands with seccomp-bpf + namespace isolation- MCP client connects via all 4 transports (stdio, SSE, HTTP, WebSocket) with OAuth 2.1- Permission system enforces 5 modes (Allow, Deny, Ask, Skip, Review) with wildcard patterns- Background tasks run async with progress reporting- Hook system fires 9+ events with registered handlers- Git worktree isolation tested for concurrent sessions |
| Duration Estimate | 21-28 calendar days |
| Risk Level | HIGH – Sandboxed execution security is mission-critical; MCP OAuth complexity; permission system must not lock users out |
| Rollback Strategy | - SANDBOX_MODE=disabled for emergency fallback- Permission default is ask (never deny by default)- MCP can be disabled per-transport- Plan mode has auto-approve opt-in only |

Phase 4: UI/UX & TUI – Streaming TUI, Themes, Terminal Intellisense

| Attribute | Detail |
| --- | --- |
| Phase Goal | Transform the HelixCode user interface into a best-in-class TUI with streaming updates, theme support, terminal intellisense (Amazon Q style), AskUserQuestion with previews (Claude Code), cumulative diff review (Plandex), and no-flicker rendering across all 6 supported platforms. |
| Entry Criteria | - Phase 3 exit criteria met- UI rendering pipeline benchmarked- Theme asset pipeline defined- Terminal capability detection library chosen |
| Exit Criteria | - Streaming TUI renders token-by-token with <50ms latency- Theme system applies 6 platform themes + custom themes- Terminal intellisense suggests commands with 85%+ relevance- AskUserQuestion renders file previews, diffs, and images- Cumulative diff review allows accept/reject per hunk- No-flicker rendering verified on: Linux terminal, macOS terminal, Windows Terminal, VS Code terminal, JetBrains terminal, iTerm2 |
| Duration Estimate | 14-18 calendar days |
| Risk Level | MEDIUM – Cross-platform terminal behavior variance; theme asset maintenance |
| Rollback Strategy | - UI_MODE=simple falls back to basic output- Themes can be disabled with THEME=none- Terminal intellisense is opt-in (--intellisense) |

Phase 5: Testing & QA – 100% Coverage, Challenges, HelixQA Sessions

| Attribute | Detail |
| --- | --- |
| Phase Goal | Achieve production readiness through comprehensive testing: 100% code coverage on all new code, HelixQA automated challenge sessions, LLMsVerifier integration for model output validation, Containers-based integration testing, and performance benchmarking against baselines. |
| Entry Criteria | - Phase 4 exit criteria met- Test infrastructure can execute containerized tests- Challenge dataset prepared (>= 50 challenges)- Performance benchmarks defined |
| Exit Criteria | - go test -cover reports >= 100% for all new packages- HelixQA completes >= 50 challenge sessions with >90% pass rate- LLMsVerifier validates model outputs with <5% false positive rate- Integration tests run in Containers with full feature matrix- Performance benchmarks meet all p95 targets- Security audit of sandboxed execution passes- Load test: 100 concurrent sessions stable for 1 hour |
| Duration Estimate | 14-18 calendar days |
| Risk Level | MEDIUM – 100% coverage is time-consuming; challenge flakiness; load test infrastructure |
| Rollback Strategy | - Coverage gates can be temporarily lowered to 95% with technical debt ticket- Challenges can be rerun; flaky tests are quarantined- Load tests run on staging environment only |

Section 3: DETAILED TASKS PER PHASE

Phase 0: Foundation – Submodule Integration & Build System Fix

P0-T1: Audit Current Submodule State

- Task ID: P0-T1

- Task Name: Complete Submodule Audit and Inventory

- Description: Catalog all 87 existing submodules, identify which are initialized, which have SSH URL issues, which have diverged from expected commits. Document the circular dependency between HelixCode (child) and HelixAgent (parent).

- Dependencies: None

- Estimated Effort: 1 day

- Submodule(s) Involved: HelixCode (all 87 submodules)

- Files/Modules to Modify: SUBMODULE_AUDIT.md (new document)

- Acceptance Criteria: Complete inventory table with 87 submodules showing: name, path, current commit, initialized status, SSH URL, last update date, build status.

P0-T2: Add Missing Submodules

- Task ID: P0-T2

- Task Name: Add HelixAgent, HelixLLM, HelixMemory, HelixSpecifier Submodules

- Description: Add the 4 missing submodules as SSH-based git submodules at the correct paths. Handle the special case where HelixAgent is a parent/ancestor of HelixCode by using relative paths or explicit SSH URLs.

- Dependencies: P0-T1

- Estimated Effort: 1 day

- Submodule(s) Involved: HelixAgent, HelixLLM, HelixMemory, HelixSpecifier

- Files/Modules to Modify: .gitmodules, .git/config (local)

- Acceptance Criteria: git submodule status shows all 4 new submodules; git submodule update --init --recursive clones all 4 successfully; no SSH key prompts during CI.

P0-T3: Initialize Dormant Submodules

- Task ID: P0-T3

- Task Name: Initialize LLMsVerifier, HelixQA, Challenges, Containers

- Description: The 4 present-but-uninitialized submodules need to be initialized and their builds verified. Check if they have independent build requirements (e.g., Containers may need Docker, HelixQA may need test datasets).

- Dependencies: P0-T2

- Estimated Effort: 1 day

- Submodule(s) Involved: LLMsVerifier, HelixQA, Challenges, Containers

- Files/Modules to Modify: .gitmodules (update init paths if needed), submodule README.md files

- Acceptance Criteria: All 4 submodules show init status; each submodule’s go build ./... (or equivalent) succeeds.

P0-T4: Create Go Workspace

- Task ID: P0-T4

- Task Name: Unify Build System with Go Workspaces

- Description: Create a go.work file at HelixCode root that includes all submodules with Go code. Resolve any module path conflicts, replace directives, or version mismatches. Ensure the workspace builds from a clean environment.

- Dependencies: P0-T2, P0-T3

- Estimated Effort: 2 days

- Submodule(s) Involved: All Go-based submodules

- Files/Modules to Modify: go.work (new), go.work.sum (generated), individual go.mod files if version alignment needed

- Acceptance Criteria: go work sync completes without errors; go build ./... from HelixCode root builds all modules; go test ./... runs all tests.

P0-T5: CI Pipeline for Submodule Matrix

- Task ID: P0-T5

- Task Name: GitHub Actions CI for Submodule Build Matrix

- Description: Create or update GitHub Actions workflows to build and test across all submodules on Linux, macOS, and Windows. Include SSH key setup for private submodule access.

- Dependencies: P0-T4

- Estimated Effort: 2 days

- Submodule(s) Involved: All (CI configuration)

- Files/Modules to Modify: .github/workflows/ci.yml (new or updated), .github/workflows/submodule-check.yml

- Acceptance Criteria: CI passes for all 11 submodules on all 3 OS platforms; submodule drift detection job runs daily.

Phase 1: Core Infrastructure – LLM Gateway, Memory, Spec Engine

P1-T1: LLM Gateway Interface Design

- Task ID: P1-T1

- Task Name: Define Unified LLM Provider Interface

- Description: Design the LLMGateway interface that abstracts all 29+ existing providers and prepares for 75+ (OpenCode-style). Must support: completion, streaming, tool calling, multi-modal input, context window querying, and provider capability discovery.

- Dependencies: P0-T5 (workspace ready)

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixLLM, HelixCode (internal LLM factory)

- Files/Modules to Modify: pkg/llm/gateway.go (new), pkg/llm/provider.go (new), pkg/llm/capability.go (new)

- Acceptance Criteria: Interface compiles; mock implementation passes; 29 existing providers can be adapted to interface.

P1-T2: Multi-Provider Backend Integration

- Task ID: P1-T2

- Task Name: Integrate 75+ Provider Support with Mid-Session Switching

- Description: Port OpenCode’s provider registry to HelixCode. Implement dynamic provider loading, configuration per provider (API keys, base URLs, timeouts), and mid-session model switching. Add provider health checking.

- Dependencies: P1-T1

- Estimated Effort: 4 days

- Submodule(s) Involved: HelixLLM, OpenCode (reference)

- Files/Modules to Modify: pkg/llm/registry.go, pkg/llm/provider_*.go (one per provider family), pkg/llm/switch.go, config/providers.yaml

- Acceptance Criteria: Can list 75+ providers; can switch provider mid-conversation without losing context; health check returns status for each provider.

P1-T3: Provider Wizard and Configuration

- Task ID: P1-T3

- Task Name: Multi-Provider Backend Wizards

- Description: Interactive CLI wizards (Cobra-based) for configuring new providers. Prompt for API keys, test connectivity, save to Viper config. Support OAuth flows for providers requiring it.

- Dependencies: P1-T2

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode (CLI)

- Files/Modules to Modify: cmd/llm/wizard.go, cmd/llm/configure.go, pkg/config/provider.go

- Acceptance Criteria: helixcode llm configure --provider openai completes interactively; config persists; connection test passes.

P1-T4: Memory System Schema and Storage

- Task ID: P1-T4

- Task Name: PostgreSQL Schema for Conversation Memory

- Description: Design and implement PostgreSQL schema for persistent memory: conversations, messages, embeddings, session state, and context windows. Use pgvector for embedding storage.

- Dependencies: P0-T5

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixMemory

- Files/Modules to Modify: migrations/001_memory.up.sql, migrations/001_memory.down.sql, pkg/memory/schema.go, pkg/memory/store.go

- Acceptance Criteria: Migrations apply cleanly; pgvector extension enabled; CRUD operations on all tables pass.

P1-T5: Embedding and Retrieval Engine

- Task ID: P1-T5

- Task Name: Semantic Search with Embeddings

- Description: Integrate embedding generation (via HelixLLM or local model) and semantic retrieval. Implement conversation context retrieval, file similarity search, and cross-session memory. Support HNSW indexing.

- Dependencies: P1-T4, P1-T2

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixMemory, HelixLLM

- Files/Modules to Modify: pkg/memory/embed.go, pkg/memory/search.go, pkg/memory/index.go

- Acceptance Criteria: Can store 1000 conversation fragments and retrieve top-5 relevant in <100ms; embedding dimension matches model output.

P1-T6: Spec Engine Core

- Task ID: P1-T6

- Task Name: Task Decomposition and Specification Engine

- Description: Build HelixSpecifier core: parse user intent, decompose into subtasks, generate specifications for each subtask. Uses LLM with structured output (JSON schema) for reliable decomposition.

- Dependencies: P1-T2

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixSpecifier

- Files/Modules to Modify: pkg/spec/engine.go, pkg/spec/decomposer.go, pkg/spec/validator.go, pkg/spec/schema.go

- Acceptance Criteria: “Implement a REST API with auth” decomposes into >= 3 subtasks with clear inputs/outputs; decomposition succeeds 90% of time on benchmark prompts.

P1-T7: Redis Context Cache

- Task ID: P1-T7

- Task Name: Redis-Based Context Window Caching

- Description: Implement Redis data structures for caching LLM context windows, provider responses, and embedding vectors. Configure TTL policies and eviction strategies.

- Dependencies: P1-T4

- Estimated Effort: 1 day

- Submodule(s) Involved: HelixCode (Redis layer)

- Files/Modules to Modify: pkg/cache/redis.go, pkg/cache/context.go, pkg/cache/ttl.go

- Acceptance Criteria: Context cache hit reduces LLM call latency by >= 50%; TTL eviction works; Redis memory usage bounded.

P1-T8: OpenAPI Spec Update for Core APIs

- Task ID: P1-T8

- Task Name: Expand OpenAPI 3.0 Spec for New Endpoints

- Description: Add /api/v1/llm/*, /api/v1/memory/*, /api/v1/spec/* endpoints to the OpenAPI specification. Generate handler stubs and client SDK updates.

- Dependencies: P1-T1, P1-T4, P1-T6

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode (Gin server)

- Files/Modules to Modify: api/openapi.yaml, pkg/api/handlers_llm.go, pkg/api/handlers_memory.go, pkg/api/handlers_spec.go

- Acceptance Criteria: openapi-generator produces valid client; all new endpoints documented; handler stubs compile.

Phase 2: CLI Agent Foundation – Tool Framework, Context Management, Edit System

P2-T1: Tool Framework Core

- Task ID: P2-T1

- Task Name: Pluggable Tool Framework with Registration/Discovery

- Description: Implement a tool framework where each tool is a self-describing plugin with JSON schema for inputs/outputs. Tools register at startup, support validation, execution, and result formatting. Inspired by Claude Code’s tool system.

- Dependencies: P1-T2 (LLM gateway ready)

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixCode (core), HelixAgent (reference)

- Files/Modules to Modify: pkg/tool/framework.go, pkg/tool/registry.go, pkg/tool/executor.go, pkg/tool/schema.go, pkg/tool/builtin/*.go

- Acceptance Criteria: >= 10 tools registered; tool discovery API lists all tools; tool execution returns structured results; schema validation rejects invalid inputs.

P2-T2: Built-in Tool Suite

- Task ID: P2-T2

- Task Name: Implement Core Tool Suite (Read, Edit, Bash, Git, Search, LS, Glob, Ask, Done)

- Description: Build the essential tools every code agent needs: file read/write, directory listing, glob search, grep search, bash execution, git operations, user ask, and task completion signaling.

- Dependencies: P2-T1

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/tool/read.go, pkg/tool/edit.go, pkg/tool/bash.go, pkg/tool/git.go, pkg/tool/search.go, pkg/tool/ls.go, pkg/tool/glob.go, pkg/tool/ask.go, pkg/tool/done.go

- Acceptance Criteria: Each tool has unit tests; integration test exercises all tools in sequence; tool results are serializable to JSON.

P2-T3: Tool Result Persistence

- Task ID: P2-T3

- Task Name: Persist Tool Results to PostgreSQL

- Description: Store all tool invocations, inputs, outputs, and execution timestamps in PostgreSQL. Support querying tool history by session, by tool type, and by time range.

- Dependencies: P2-T2, P1-T4

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixMemory

- Files/Modules to Modify: pkg/tool/persistence.go, migrations/002_tool_results.up.sql, pkg/tool/history.go

- Acceptance Criteria: Every tool call stored; query by session returns chronological list; no duplicate storage of identical calls.

P2-T4: Context Window Manager

- Task ID: P2-T4

- Task Name: Context Window Tracking and Limits

- Description: Track token usage per provider, per model, per session. Enforce context window limits and provide warnings at 80%, 90%, 95% thresholds.

- Dependencies: P1-T2, P1-T7

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/context/window.go, pkg/context/tokenizer.go, pkg/context/limits.go

- Acceptance Criteria: Accurate token counting (within 5% of provider count); warnings fire at correct thresholds; hard limit prevents overflow.

P2-T5: Auto-Compaction System

- Task ID: P2-T5

- Task Name: Semantic Context Compaction (Codex + Plandex Style)

- Description: Implement automatic context compaction when approaching token limits. Strategy: summarize older conversation turns, compress file contents with Tree-sitter structural summaries, and evict least-relevant context based on embedding similarity.

- Dependencies: P2-T4, P1-T5, P1-T7

- Estimated Effort: 4 days

- Submodule(s) Involved: HelixCode, HelixLLM, HelixMemory

- Files/Modules to Modify: pkg/context/compactor.go, pkg/context/summarizer.go, pkg/context/relevance.go

- Acceptance Criteria: 2M token context compacted to 128k with <5% semantic loss (measured by QA task accuracy); compaction time <2s.

P2-T6: Smart File Editing with Fuzzy Matching

- Task ID: P2-T6

- Task Name: 4-Layer Fuzzy Matching Edit System (Aider-Inspired)

- Description: Implement Aider’s 4-layer approach: (1) exact match, (2) normalized whitespace match, (3) indent-ignoring match, (4) AI-guided fuzzy match. Apply edits with confidence scoring and fallback to user confirmation.

- Dependencies: P2-T2 (edit tool), P1-T6 (spec engine for guidance)

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixCode, HelixAgent

- Files/Modules to Modify: pkg/edit/matcher.go (4 layers), pkg/edit/applier.go, pkg/edit/confidence.go

- Acceptance Criteria: 99%+ accuracy on exact match test corpus; 95%+ on fuzzy match corpus; <0.1% data loss incidents.

P2-T7: No-Flicker Rendering Engine

- Task ID: P2-T7

- Task Name: Terminal Rendering with No Flicker (Claude Code Style)

- Description: Implement buffered terminal output that computes minimal diff between frames and renders only changed regions. Use terminal capability detection (CSI queries) for feature selection.

- Dependencies: P2-T6

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode (UI layer)

- Files/Modules to Modify: pkg/render/buffer.go, pkg/render/diff.go, pkg/render/terminal.go, pkg/render/capabilities.go

- Acceptance Criteria: 60 FPS render of streaming text with zero visible flicker on tested terminals; falls back gracefully on dumb terminals.

P2-T8: Session Transcript and Resume

- Task ID: P2-T8

- Task Name: Session Transcript Persistence and Resume (Claude Code Style)

- Description: Persist full session transcripts (user inputs, AI responses, tool calls, results) to PostgreSQL. Support resuming a session from any point with full context restoration.

- Dependencies: P2-T3, P1-T4

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixMemory

- Files/Modules to Modify: pkg/session/transcript.go, pkg/session/resume.go, pkg/session/serialize.go

- Acceptance Criteria: Session saved after every turn; resume restores identical context; 100 sessions can be listed and selected.

P2-T9: Background Task System

- Task ID: P2-T9

- Task Name: Async Background Task Execution

- Description: Allow tasks (tool calls, file operations, LLM requests) to run in background with progress reporting. Support task cancellation, prioritization, and result notification.

- Dependencies: P2-T1, P1-T7

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/task/manager.go, pkg/task/worker.go, pkg/task/progress.go, pkg/task/cancel.go

- Acceptance Criteria: Task submitted and runs async; progress updates stream to UI; cancellation stops task; results delivered when complete.

Phase 3: Power Features – Plan Mode, Sandboxing, MCP, Permissions

P3-T1: Plan Mode Engine

- Task ID: P3-T1

- Task Name: Plan/Act Dual Mode with Different Models (Cline + Gemini CLI Style)

- Description: Implement Plan mode where a planning model (e.g., o1, Claude 3.5 Sonnet) generates a step-by-step plan, and an acting model (e.g., Claude 3.5 Haiku, GPT-4o-mini) executes each step. Plan must be user-editable and require approval before execution.

- Dependencies: P1-T6 (spec engine), P1-T2 (multi-provider), P2-T9 (background tasks)

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixCode, HelixSpecifier

- Files/Modules to Modify: pkg/plan/engine.go, pkg/plan/approval.go, pkg/plan/executor.go, pkg/plan/state.go

- Acceptance Criteria: Plan generated with >= 3 steps for complex requests; user can edit plan; approval gates prevent auto-execution; different models selectable for plan vs act.

P3-T2: Cumulative Diff Review Sandbox

- Task ID: P3-T2

- Task Name: Diff Review Sandbox with Per-Hunk Approval (Plandex Style)

- Description: Collect all file changes across a session into a cumulative diff. Present hunks for review with accept/reject/edit options. Maintain a sandbox branch until changes are approved.

- Dependencies: P2-T6 (smart edit), P3-T1 (plan mode)

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/diff/sandbox.go, pkg/diff/review.go, pkg/diff/hunk.go, pkg/diff/approval.go

- Acceptance Criteria: Changes accumulate across session; diff renders with syntax highlighting; accept/reject per hunk works; rejected hunks excluded from final patch.

P3-T3: Shadow Git Checkpoints

- Task ID: P3-T3

- Task Name: Automatic Git Checkpoints Before Every Change (Cline Style)

- Description: Create lightweight git checkpoints (branches or stashes) before every file modification. Support checkpoint restore, diff between checkpoints, and checkpoint history navigation.

- Dependencies: P2-T2 (git tool)

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/git/checkpoint.go, pkg/git/restore.go, pkg/git/history.go

- Acceptance Criteria: Checkpoint created before each edit; restore returns to exact prior state; checkpoint list navigable; no impact on user’s main branch.

P3-T4: Git Worktree Isolation

- Task ID: P3-T4

- Task Name: Git Worktree Isolation for Concurrent Sessions (Claude Code Style)

- Description: Use git worktrees to isolate concurrent agent sessions. Each session gets its own worktree with independent file state, preventing cross-session interference.

- Dependencies: P3-T3

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/git/worktree.go, pkg/session/isolation.go

- Acceptance Criteria: 5 concurrent sessions each in own worktree; changes in one don’t affect others; worktree cleanup on session end.

P3-T5: Sandboxed Shell Execution Core

- Task ID: P3-T5

- Task Name: Container-Based Sandboxed Shell (Claude Code + Codex Style)

- Description: Implement containerized command execution using Docker/Podman. Each shell command runs in a fresh container with limited filesystem access, network restrictions, and timeout enforcement.

- Dependencies: P0-T5 (containers submodule), P2-T2 (bash tool)

- Estimated Effort: 4 days

- Submodule(s) Involved: Containers, HelixCode

- Files/Modules to Modify: pkg/sandbox/container.go, pkg/sandbox/executor.go, pkg/sandbox/policy.go, pkg/sandbox/network.go, pkg/sandbox/fs.go

- Acceptance Criteria: ls -la runs in container; network-restricted container cannot curl; timeout kills after limit; filesystem only sees mounted project directory.

P3-T6: OS-Native Sandboxed Execution

- Task ID: P3-T6

- Task Name: seccomp-bpf + Namespace Sandboxing for Native Performance (Codex Style)

- Description: For local execution without Docker, implement Linux-native sandboxing using seccomp-bpf system call filtering, PID namespaces, mount namespaces, and capability dropping. macOS uses seatbelt/entitlements equivalent.

- Dependencies: P3-T5

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/sandbox/seccomp.go, pkg/sandbox/namespace.go, pkg/sandbox/native.go

- Acceptance Criteria: execve blocked by seccomp; process cannot access files outside project; setuid calls fail; sandbox overhead <50ms per command.

P3-T7: Permission Rule System

- Task ID: P3-T7

- Task Name: 5-Mode Permission System with Wildcards (Claude Code Style)

- Description: Implement permission rules with 5 modes: Allow (auto-execute), Deny (block), Ask (prompt user), Skip (silently ignore), Review (queue for batch review). Support wildcard patterns for file paths, command patterns, and tool types. Configurable per-directory, per-session, or globally.

- Dependencies: P2-T1 (tool framework), P3-T5 (sandbox)

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/permission/engine.go, pkg/permission/rule.go, pkg/permission/matcher.go, pkg/permission/mode.go, config/permissions.yaml

- Acceptance Criteria: All 5 modes tested; wildcard *.log matches correctly; rule precedence resolved (most specific wins); permission prompt rendered in TUI.

P3-T8: MCP Client Lifecycle

- Task ID: P3-T8

- Task Name: MCP Client with 4 Transports + OAuth (Claude Code Style)

- Description: Implement Model Context Protocol client supporting 4 transports: stdio (local process), SSE (server-sent events), HTTP (direct REST), WebSocket (bidirectional). Include full OAuth 2.1 PKCE flow for authentication.

- Dependencies: P1-T2 (provider system), P2-T1 (tool framework)

- Estimated Effort: 5 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/mcp/client.go, pkg/mcp/transport_stdio.go, pkg/mcp/transport_sse.go, pkg/mcp/transport_http.go, pkg/mcp/transport_ws.go, pkg/mcp/oauth.go, pkg/mcp/discovery.go

- Acceptance Criteria: Connects to MCP server via each transport; OAuth flow completes; tool discovery lists remote tools; remote tool execution returns results.

P3-T9: Hook-Based Extensibility

- Task ID: P3-T9

- Task Name: 9+ Event Hook System (Claude Code Style)

- Description: Implement a hook system firing events at key lifecycle points: before_request, after_request, before_tool_call, after_tool_call, before_edit, after_edit, on_plan, on_approval, on_error, on_session_start, on_session_end. Support pre- and post-hooks with cancellation.

- Dependencies: P2-T1, P3-T7

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/hook/engine.go, pkg/hook/events.go, pkg/hook/handler.go

- Acceptance Criteria: All 11 hooks fire at correct times; pre-hook can cancel operation; post-hook receives full context; handler registration is dynamic.

P3-T10: Skill System

- Task ID: P3-T10

- Task Name: Skill Definition and Loading System (Claude Code Style)

- Description: Skills are YAML/JSON bundles defining: prompt templates, tool configurations, permission rules, model preferences, and hooks. Load skills from filesystem or remote URL. Support skill versioning and dependencies.

- Dependencies: P3-T9, P3-T7

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/skill/loader.go, pkg/skill/schema.go, pkg/skill/manager.go, pkg/skill/version.go

- Acceptance Criteria: Skill loaded from YAML; tools configured by skill; permissions overridden by skill; skill dependency resolved.

P3-T11: Subagent Team System

- Task ID: P3-T11

- Task Name: Subagent Team Delegation (Claude Code + Kilo Code Style)

- Description: Create specialized subagent types: Researcher (finds information), Editor (makes file changes), Reviewer (checks quality), Tester (runs tests), Architect (designs structure). Orchestrate via a meta-agent that delegates tasks.

- Dependencies: P3-T1, P1-T6, P2-T9

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/agent/roles.go, pkg/agent/orchestrator.go, pkg/agent/delegator.go, pkg/agent/communicator.go

- Acceptance Criteria: 5 subagent types defined; meta-agent delegates to correct specialist; inter-agent communication works; results aggregated.

P3-T12: Computer Use / Browser Automation

- Task ID: P3-T12

- Task Name: Browser Automation for Computer Use (Cline Style)

- Description: Integrate browser automation (Playwright/CDP) for computer use capabilities: navigate URLs, click elements, fill forms, take screenshots, and extract content. Return results as tool outputs.

- Dependencies: P2-T1 (tool framework)

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/tool/browser.go, pkg/browser/controller.go, pkg/browser/screenshot.go

- Acceptance Criteria: Can navigate to URL and click element; screenshot returned as base64; form fill works; headless mode default.

P3-T13: Quality Scoring and Automated Gates

- Task ID: P3-T13

- Task Name: Quality Scoring with Automated Pass/Fail Gates (Forge Style)

- Description: Implement quality metrics for agent outputs: code style, test coverage, static analysis score, security scan, performance benchmark. Gate plan execution on quality thresholds.

- Dependencies: P3-T1, P2-T6

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode, HelixQA

- Files/Modules to Modify: pkg/quality/scorer.go, pkg/quality/gate.go, pkg/quality/metrics.go

- Acceptance Criteria: Score computed for code output; gate blocks low-quality changes; metric definitions extensible.

P3-T14: OpenTelemetry Integration

- Task ID: P3-T14

- Task Name: Distributed Tracing and Metrics (Claude Code Style)

- Description: Integrate OpenTelemetry for tracing all major flows: LLM requests, tool calls, file edits, plan steps, MCP operations. Export to Jaeger/Zipkin and Prometheus.

- Dependencies: P1-T2, P3-T8

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/telemetry/tracer.go, pkg/telemetry/metrics.go, pkg/telemetry/provider.go

- Acceptance Criteria: Trace spans cover all major operations; p95 latency measured; metrics exported; sampling configurable.

Phase 4: UI/UX & TUI – Streaming TUI, Themes, Terminal Intellisense

P4-T1: Streaming TUI Core

- Task ID: P4-T1

- Task Name: Token-Streaming TUI with Markdown Rendering

- Description: Build a TUI that streams LLM output token-by-token, renders markdown (code blocks, lists, tables), and handles concurrent tool output streams. Support split-pane view (conversation + tool output).

- Dependencies: P2-T7 (no-flicker render), P3-T5 (sandbox output)

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/tui/stream.go, pkg/tui/markdown.go, pkg/tui/layout.go, pkg/tui/pane.go

- Acceptance Criteria: Tokens render within 50ms of arrival; markdown code blocks syntax highlighted; split pane resizable; 60 FPS maintained.

P4-T2: Theme System

- Task ID: P4-T2

- Task Name: 6-Platform Theme System with Custom Themes (Claude Code Style)

- Description: Implement a theme engine supporting: Linux terminal (16/256/truecolor), macOS Terminal.app, Windows Terminal, VS Code integrated terminal, JetBrains terminal, iTerm2. Detect terminal capabilities and adapt. Support custom theme YAML files.

- Dependencies: P2-T7 (terminal capabilities)

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/theme/engine.go, pkg/theme/palette.go, pkg/theme/platforms.go, pkg/theme/custom.go, themes/*.yaml

- Acceptance Criteria: Each platform renders with correct colors; custom theme loads and applies; theme switch without restart.

P4-T3: AskUserQuestion with Previews

- Task ID: P4-T3

- Task Name: Interactive User Prompts with File/Diff/Image Previews (Claude Code Style)

- Description: Enhanced AskUserQuestion tool that renders rich previews: file contents with syntax highlighting, diffs with color coding, images in supported terminals (iTerm2 inline, sixel, kitty graphics). Support keyboard navigation and quick actions.

- Dependencies: P4-T1, P4-T2, P2-T2 (ask tool)

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/tui/ask.go, pkg/tui/preview_file.go, pkg/tui/preview_diff.go, pkg/tui/preview_image.go

- Acceptance Criteria: File preview renders with syntax highlight; diff preview shows colors; image preview works in iTerm2/kitty; keyboard navigation intuitive.

P4-T4: Terminal Intellisense

- Task ID: P4-T4

- Task Name: Fig-Style Terminal Intellisense (Amazon Q Style)

- Description: Provide command-line completion suggestions as you type, showing: available commands, file paths, git branches, recent commands, and contextual suggestions based on current directory contents. Render in a floating popup.

- Dependencies: P4-T1

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/tui/intellisense.go, pkg/tui/completion.go, pkg/tui/popup.go, pkg/tui/context.go

- Acceptance Criteria: Suggestions appear within 100ms of typing; file path completion works; git branch completion works; popup renders correctly; 85%+ relevance score.

P4-T5: Slash Command System

- Task ID: P4-T5

- Task Name: Slash Command Registry and Execution (Claude Code Style)

- Description: Implement /command system where commands like /compact, /memory, /undo, /help, /model are registered and executed. Commands have completions, help text, and argument parsing.

- Dependencies: P4-T4, P2-T1 (tool framework)

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/slash/registry.go, pkg/slash/executor.go, pkg/slash/builtins.go, pkg/slash/completion.go

- Acceptance Criteria: >= 15 slash commands registered; tab completion works; help text displayed; arguments parsed correctly.

P4-T6: Architect/Editor Dual-Model UI

- Task ID: P4-T6

- Task Name: Dual-Model UI for Architect/Editor Mode (Aider Style)

- Description: UI mode showing both architect model reasoning and editor model output side by side. Architect view shows design rationale; editor view shows implementation. Support switching focus between views.

- Dependencies: P4-T1, P3-T1

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/tui/dual_model.go, pkg/tui/architect_pane.go, pkg/tui/editor_pane.go

- Acceptance Criteria: Architect reasoning visible; editor code visible; dual pane layout correct; focus switch works.

P4-T7: Multi-Agent Platform State Machine UI

- Task ID: P4-T7

- Task Name: Agent State Machine Visualization (Kilo Code Style)

- Description: Visualize the multi-agent state machine: show current state (Idle, Planning, Executing, Reviewing, Error), agent assignments, and transitions. Support manual state override.

- Dependencies: P3-T11, P4-T1

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/tui/state_machine.go, pkg/tui/agent_status.go, pkg/tui/transition.go

- Acceptance Criteria: Current state clearly shown; agent assignments listed; state transitions animated; manual override works.

P4-T8: LSP Integration with Diagnostics

- Task ID: P4-T8

- Task Name: LSP Client for Diagnostics Feedback (OpenCode Style)

- Description: Integrate LSP client for receiving real-time diagnostics from language servers. Show errors, warnings, and suggestions inline. Support multiple concurrent LSP servers.

- Dependencies: P4-T1, P2-T6

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/lsp/client.go, pkg/lsp/diagnostics.go, pkg/lsp/server_manager.go, pkg/lsp/inline.go

- Acceptance Criteria: LSP connection established; diagnostics displayed inline; multi-server support; <1s roundtrip.

P4-T9: Multimodal Input Processing

- Task ID: P4-T9

- Task Name: Image and File Attachment in Prompts (Gemini CLI Style)

- Description: Support multimodal input: drag-and-drop image files, paste images from clipboard, attach PDFs or text files to prompts. Process with vision-capable models.

- Dependencies: P4-T1, P1-T2

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/input/multimodal.go, pkg/input/image.go, pkg/input/clipboard.go, pkg/input/attachment.go

- Acceptance Criteria: Image attached and sent to vision model; PDF text extracted; clipboard image pasted; attachment size limits enforced.

P4-T10: 1M+ Token Context Window UI

- Task ID: P4-T10

- Task Name: Large Context Window Indicator and Management (Gemini CLI Style)

- Description: UI components for managing 1M+ token contexts: context usage bar, file inclusion manager, context window visualization, and token budget allocation per file.

- Dependencies: P2-T4, P2-T5

- Estimated Effort: 1 day

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: pkg/tui/context_bar.go, pkg/tui/context_manager.go, pkg/tui/token_budget.go

- Acceptance Criteria: Context bar accurate; file inclusion toggle works; budget allocation visible; 1M tokens handled without UI lag.

Phase 5: Testing & QA – 100% Coverage, Challenges, HelixQA Sessions

P5-T1: Unit Test Coverage Enforcement

- Task ID: P5-T1

- Task Name: Achieve 100% Unit Test Coverage for All New Code

- Description: Write unit tests for every new function, method, and branch in Phases 1-4. Use table-driven tests, property-based tests where appropriate, and mock interfaces for external dependencies. Enforce via CI gate.

- Dependencies: All Phase 1-4 tasks

- Estimated Effort: 5 days

- Submodule(s) Involved: All

- Files/Modules to Modify: *_test.go files across all new packages

- Acceptance Criteria: go test -cover reports >= 100% for all packages modified in Phases 1-4; no test flakes in 100 consecutive runs.

P5-T2: Integration Test Suite

- Task ID: P5-T2

- Task Name: End-to-End Integration Tests in Containers

- Description: Build containerized integration tests exercising full workflows: plan -> edit -> test -> commit. Use Docker Compose for PostgreSQL + Redis + HelixCode stack. Test all major feature combinations.

- Dependencies: P5-T1, P0-T5

- Estimated Effort: 3 days

- Submodule(s) Involved: Containers, HelixCode

- Files/Modules to Modify: tests/integration/*.go, docker-compose.test.yml, .github/workflows/integration.yml

- Acceptance Criteria: >= 20 integration scenarios pass; test stack starts in <30s; tests complete in <10 minutes.

P5-T3: HelixQA Challenge Sessions

- Task ID: P5-T3

- Task Name: Automated Challenge-Based QA Testing

- Description: Configure HelixQA submodule to run >= 50 challenge sessions against the integrated HelixCode. Challenges cover: bug fixing, feature implementation, refactoring, test writing, and documentation. Track pass rate and regression rate.

- Dependencies: P0-T3 (HelixQA initialized), P5-T2

- Estimated Effort: 3 days

- Submodule(s) Involved: HelixQA, Challenges

- Files/Modules to Modify: helixqa/challenges/*.yaml, helixqa/runner.go, .github/workflows/helixqa.yml

- Acceptance Criteria: >= 50 challenges defined; >90% pass rate; challenge results stored; regression detection automated.

P5-T4: LLMsVerifier Integration

- Task ID: P5-T4

- Task Name: Model Output Verification and Consistency Checks

- Description: Integrate LLMsVerifier to validate LLM outputs: check for hallucinations, verify code correctness, detect harmful content, and measure output consistency across providers. Use for both regression testing and runtime validation.

- Dependencies: P0-T3 (LLMsVerifier initialized), P1-T2

- Estimated Effort: 2 days

- Submodule(s) Involved: LLMsVerifier, HelixCode

- Files/Modules to Modify: pkg/verify/llmverifier.go, pkg/verify/hallucination.go, pkg/verify/consistency.go

- Acceptance Criteria: Hallucination detection <5% false positive; consistency score computed; verifier runs in CI; runtime validation optional.

P5-T5: Security Audit – Sandboxed Execution

- Task ID: P5-T5

- Task Name: Penetration Testing for Sandbox Escape

- Description: Hire/engage security team to attempt sandbox escape from containerized and seccomp-based sandboxes. Test vectors: privilege escalation, filesystem breakout, network tunneling, resource exhaustion, and side-channel attacks.

- Dependencies: P3-T5, P3-T6

- Estimated Effort: 3 days

- Submodule(s) Involved: Containers, HelixCode

- Files/Modules to Modify: security/audit/sandbox_escape_tests.go (new)

- Acceptance Criteria: No sandbox escapes found; all test vectors contained; security report generated and signed off.

P5-T6: Performance Benchmarking

- Task ID: P5-T6

- Task Name: Establish and Validate Performance Baselines

- Description: Create benchmark suite measuring: p95 edit latency, p95 plan generation time, p95 context compaction time, throughput (requests/sec), memory usage under load. Run against baselines and fail on regression >10%.

- Dependencies: All Phase 1-4 tasks

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: tests/benchmark/*.go, .github/workflows/benchmark.yml

- Acceptance Criteria: All p95 targets met; benchmarks run in CI; regression alerts configured; results dashboard accessible.

P5-T7: Load and Stress Testing

- Task ID: P5-T7

- Task Name: 100 Concurrent Session Load Test

- Description: Run 100 concurrent agent sessions for 1 hour against the full stack. Monitor: response latency, error rate, memory leaks, goroutine leaks, database connection pool exhaustion, Redis saturation.

- Dependencies: P5-T6, P5-T2

- Estimated Effort: 2 days

- Submodule(s) Involved: HelixCode, Containers

- Files/Modules to Modify: tests/load/*.go, tests/load/scenarios.yaml

- Acceptance Criteria: 100 sessions stable for 1 hour; <1% error rate; no memory leaks detected; no goroutine growth; database and Redis healthy.

P5-T8: Plugin System Validation

- Task ID: P5-T8

- Task Name: Validate 25+ Lifecycle Hooks for Plugin System (OpenCode Style)

- Description: Test the plugin system with 25+ lifecycle hooks: plugin load, init, pre/post command, pre/post tool, pre/post edit, on error, on shutdown. Validate with sample plugins.

- Dependencies: P3-T9 (hook system), P4-T5 (slash commands)

- Estimated Effort: 1 day

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: tests/plugin/*.go, tests/plugin/sample_plugin.go

- Acceptance Criteria: All 25+ hooks tested; sample plugin loads and runs; plugin isolation verified; plugin crash doesn’t crash host.

P5-T9: A/B Testing Framework Validation

- Task ID: P5-T9

- Task Name: A/B Testing for Agent Configurations (Forge Style)

- Description: Validate the A/B testing framework: can run two agent configurations side by side, collect metrics, and statistically determine winner. Test with model selection and prompt variations.

- Dependencies: P3-T13 (quality scoring)

- Estimated Effort: 1 day

- Submodule(s) Involved: HelixCode

- Files/Modules to Modify: tests/ab/*.go, pkg/ab/framework.go

- Acceptance Criteria: A/B test runs to completion; metrics collected; statistical significance computed; winner selected correctly.

P5-T10: Documentation and Runbook

- Task ID: P5-T10

- Task Name: Integration Documentation and Operational Runbook

- Description: Write comprehensive documentation: architecture diagrams, API docs, configuration reference, troubleshooting guide, and operational runbook for on-call engineers.

- Dependencies: All previous tasks

- Estimated Effort: 2 days

- Submodule(s) Involved: All

- Files/Modules to Modify: docs/INTEGRATION.md, docs/ARCHITECTURE.md, docs/OPERATIONS.md, docs/API.md

- Acceptance Criteria: All docs reviewed and approved; architecture diagrams current; runbook covers 10 common incidents; API docs match OpenAPI spec.

Section 4: SUBMODULE INTEGRATION SPECIFICATIONS

Submodule 1: HelixAgent

| Attribute | Specification |
| --- | --- |
| Repository | git@github.com:HelixDevelopment/HelixAgent.git |
| Target Path | submodules/HelixAgent |
| Purpose | Parent/ancestor repository containing 60+ cli_agents integrations and 26+ submodules. Provides reference implementations, agent role definitions, and CLI agent patterns. |
| Special Consideration | HelixCode is itself a submodule OF HelixAgent. Adding HelixAgent as a submodule of HelixCode creates a circular dependency. Must be handled carefully. |

Exact SSH Commands

# From HelixCode root
cd /path/to/HelixCode

# Add HelixAgent as submodule (shallow clone, specific branch)
git submodule add --name HelixAgent \
  git@github.com:HelixDevelopment/HelixAgent.git \
  submodules/HelixAgent

# Configure to not recurse into HelixAgent's submodules (avoid infinite recursion)
git config submodule.HelixAgent.update none
cd submodules/HelixAgent
git submodule deinit -f .  # Prevent recursive init

# Fetch to known good commit (DO NOT checkout HelixCode's commit within HelixAgent)
git fetch origin
git checkout <TARGET_COMMIT>  # e.g., v2.3.1 or specific SHA

# Return to HelixCode root and commit .gitmodules
cd ../..
git add .gitmodules submodules/HelixAgent
git commit -m "feat: add HelixAgent submodule for cli_agent integration reference"

Integration Wiring Steps

- Read-Only Reference: HelixAgent is a READ-ONLY reference. Do NOT modify it from HelixCode.

- Code Port Pattern: When porting a feature from HelixAgent’s cli_agents:

  - Copy the relevant code into HelixCode’s pkg/ tree

  - Adapt import paths from dev.helix.agent to dev.helix.code

  - Add attribution comments referencing original source

  - Write tests for the ported code

- Interface Alignment: HelixAgent’s pkg/agent/interfaces.go should be compared with HelixCode’s actor model interfaces. Create adapter layer in pkg/agent/adapter.go if needed.

- No Build Dependency: HelixCode must build without HelixAgent submodule being present. Use build tags: //go:build helixagent_ref for code that imports from HelixAgent.

Configuration

# config/helixagent.yaml (new)
helixagent:
  enabled: true
  path: "submodules/HelixAgent"
  reference_only: true
  cli_agents_path: "submodules/HelixAgent/cli_agents"
  integrations_path: "submodules/HelixAgent/integrations"

Build System Changes

- Add submodules/HelixAgent to go.work but NOT as a use directive (it has its own go.work)

- Instead, reference specific packages via replace if absolutely necessary

- Prefer copying code over cross-module imports to avoid circular build issues

Submodule 2: HelixLLM

| Attribute | Specification |
| --- | --- |
| Repository | git@github.com:HelixDevelopment/HelixLLM.git |
| Target Path | submodules/HelixLLM |
| Purpose | Dedicated LLM provider management, model routing, prompt engineering, and token counting. Will be the PRIMARY provider of LLM capabilities, eventually replacing HelixCode’s internal factory. |

Exact SSH Commands

cd /path/to/HelixCode

# Add HelixLLM submodule
git submodule add --name HelixLLM \
  git@github.com:HelixDevelopment/HelixLLM.git \
  submodules/HelixLLM

cd submodules/HelixLLM
git fetch origin
git checkout <TARGET_COMMIT>  # e.g., v1.5.0 or specific SHA

# Initialize and update its submodules (if any)
git submodule update --init --recursive

cd ../..
git add .gitmodules submodules/HelixLLM
git commit -m "feat: add HelixLLM submodule for unified LLM provider management"

Integration Wiring Steps

- Workspace Integration: Add submodules/HelixLLM to go.work:

- use ./submodules/HelixLLM

- Interface Migration: Gradually replace pkg/llm/factory.go references with HelixLLM’s provider registry:

  - Phase 1: Add adapter pkg/llm/helixllm_adapter.go

  - Phase 2: Port provider configurations

  - Phase 3: Migrate all provider calls (Phase 1 of this plan)

- Configuration Merge: HelixLLM’s provider config should be mergeable with HelixCode’s Viper config tree. Use viper.MergeConfig() at initialization.

- API Exposure: Expose HelixLLM’s capabilities through HelixCode’s Gin server via adapter handlers.

Configuration

# config/llm.yaml (new, merged into viper)
llm:
  gateway:
    provider: "helixllm"
    timeout: 60s
    retry_policy: exponential
  helixllm:
    module_path: "submodules/HelixLLM"
    providers:
      - openai
      - anthropic
      - google
      - mistral
      # ... 75+ providers

Build System Changes

- go.work: Add use ./submodules/HelixLLM

- go.work.sum: Will be auto-generated

- CI: Build HelixLLM independently before HelixCode to catch upstream issues early

Submodule 3: HelixMemory

| Attribute | Specification |
| --- | --- |
| Repository | git@github.com:HelixDevelopment/HelixMemory.git |
| Target Path | submodules/HelixMemory |
| Purpose | Persistent conversation memory, embedding storage, semantic search, and cross-session context retrieval. Uses PostgreSQL + pgvector. |

Exact SSH Commands

cd /path/to/HelixCode

git submodule add --name HelixMemory \
  git@github.com:HelixDevelopment/HelixMemory.git \
  submodules/HelixMemory

cd submodules/HelixMemory
git fetch origin
git checkout <TARGET_COMMIT>
git submodule update --init --recursive

cd ../..
git add .gitmodules submodules/HelixMemory
git commit -m "feat: add HelixMemory submodule for persistent conversation memory"

Integration Wiring Steps

- Database Schema: HelixMemory manages its own migrations. HelixCode must:

  - Run HelixMemory migrations BEFORE starting the server

  - Use migration table prefix helixmemory_ to avoid collision with HelixCode tables

- Connection Sharing: HelixMemory and HelixCode share the same PostgreSQL instance but separate schemas if needed. Use search_path or explicit schema qualification.

- API Layer: HelixCode wraps HelixMemory’s Go API in HTTP handlers under /api/v1/memory/*

- Redis Integration: HelixMemory’s cache layer should use HelixCode’s Redis connection pool (configured in Phase 1).

Configuration

# config/memory.yaml (merged into viper)
memory:
  enabled: true
  module_path: "submodules/HelixMemory"
  database:
    schema: "helixmemory"
    migration_path: "submodules/HelixMemory/migrations"
  embedding:
    model: "text-embedding-3-large"
    dimensions: 3072
  retrieval:
    top_k: 5
    similarity_threshold: 0.85

Build System Changes

- go.work: Add use ./submodules/HelixMemory

- PostgreSQL migration runner: Update to include submodules/HelixMemory/migrations/*.sql

- Docker Compose: Add pgvector-enabled PostgreSQL image

Submodule 4: HelixSpecifier

| Attribute | Specification |
| --- | --- |
| Repository | git@github.com:HelixDevelopment/HelixSpecifier.git |
| Target Path | submodules/HelixSpecifier |
| Purpose | Task decomposition, specification generation, and structured output validation. Powers Plan Mode and the architect/editor workflow. |

Exact SSH Commands

cd /path/to/HelixCode

git submodule add --name HelixSpecifier \
  git@github.com:HelixDevelopment/HelixSpecifier.git \
  submodules/HelixSpecifier

cd submodules/HelixSpecifier
git fetch origin
git checkout <TARGET_COMMIT>
git submodule update --init --recursive

cd ../..
git add .gitmodules submodules/HelixSpecifier
git commit -m "feat: add HelixSpecifier submodule for task decomposition and planning"

Integration Wiring Steps

- LLM Dependency: HelixSpecifier needs LLM access. Route through HelixCode’s LLM gateway (Phase 1), NOT directly to providers.

- Structured Output: HelixSpecifier’s JSON schema validation should use HelixCode’s validation library (or shared library).

- Spec Storage: Generated specifications stored in HelixMemory for retrieval and version tracking.

- Plan Mode Integration: HelixSpecifier is the engine behind Plan Mode (Phase 3, P3-T1). Direct call from pkg/plan/engine.go to HelixSpecifier.

Configuration

# config/specifier.yaml (merged into viper)
specifier:
  enabled: true
  module_path: "submodules/HelixSpecifier"
  llm:
    provider: "helixllm"
    model: "claude-3-5-sonnet"
    temperature: 0.2
  decomposition:
    max_depth: 3
    min_confidence: 0.8
  validation:
    schema_strict: true
    retry_on_failure: 3

Build System Changes

- go.work: Add use ./submodules/HelixSpecifier

- If HelixSpecifier has its own LLM client, replace with adapter to HelixCode gateway

Summary of Submodule Additions

# One-shot script for all 4 submodules (run from HelixCode root)
#!/bin/bash
set -e

REPOS=(
  "git@github.com:HelixDevelopment/HelixAgent.git:submodules/HelixAgent"
  "git@github.com:HelixDevelopment/HelixLLM.git:submodules/HelixLLM"
  "git@github.com:HelixDevelopment/HelixMemory.git:submodules/HelixMemory"
  "git@github.com:HelixDevelopment/HelixSpecifier.git:submodules/HelixSpecifier"
)

for repo_spec in "${REPOS[@]}"; do
  IFS=: read -r url path <<< "$repo_spec"
  name=$(basename "$path")
  
  echo "=== Adding $name ==="
  git submodule add --name "$name" "$url" "$path"
  
  cd "$path"
  git fetch origin
  # NOTE: Replace <TARGET_COMMIT> with actual commit after audit
  git checkout <TARGET_COMMIT>
  git submodule update --init --recursive || true
  cd ../..
done

# Update go.work
cat >> go.work <<EOF
use ./submodules/HelixLLM
use ./submodules/HelixMemory
use ./submodules/HelixSpecifier
# HelixAgent NOT added to go.work (circular dependency, read-only reference)
EOF

git add .gitmodules go.work
git commit -m "feat: add HelixLLM, HelixMemory, HelixSpecifier submodules; HelixAgent as reference"

Section 5: DEPENDENCY GRAPH

5.1 Visual Representation

PHASE 0: FOUNDATION
===================
[P0-T1] Audit Submodules
    |
    v
[P0-T2] Add Missing Submodules --+---------------+
    |                            |
    v                            |
[P0-T3] Initialize Dormant       |
    |                            |
    v                            |
[P0-T4] Create Go Workspace -----+
    |                            |
    v                            |
[P0-T5] CI Pipeline -------------+
              |
              v
PHASE 1: CORE INFRASTRUCTURE
==============================
[P1-T1] LLM Gateway Interface
    |
    v
[P1-T2] 75+ Provider Support --+-------+
    |                          |       |
    v                          v       v
[P1-T3] Provider Wizards   [P1-T6] Spec Engine ---+
    |                          |                  |
    v                          v                  v
[P1-T8] OpenAPI Update <----+ [P1-T7] Redis Cache |
    |                         ^                    |
    |                         |                    |
[P1-T4] Memory Schema -------+ [P1-T5] Embedding    |
    |                                              |
    v                                              |
PHASE 2: CLI AGENT FOUNDATION
==============================
[P2-T1] Tool Framework <--------------------------+
    |
    v
[P2-T2] Built-in Tool Suite ----+
    |                          |
    v                          v
[P2-T3] Tool Persistence    [P2-T4] Context Window
    |                          |
    v                          v
[P2-T8] Session Resume <----+ [P2-T5] Auto-Compaction
    |                          |
    v                          v
[P2-T9] Background Tasks   [P2-T6] Smart File Editing
                                |
                                v
                           [P2-T7] No-Flicker Rendering
                                |
                                v
PHASE 3: POWER FEATURES
=========================
[P3-T1] Plan Mode <-------------------------+
    |                                       |
    v                                       |
[P3-T2] Diff Review Sandbox               |
    |                                       |
    v                                       |
[P3-T3] Shadow Git Checkpoints            |
    |                                       |
    v                                       |
[P3-T4] Git Worktree Isolation            |
    |                                       |
    v                                       v
[P3-T5] Container Sandbox ---+          [P3-T11] Subagent Team
    |                        |              |
    v                        v              v
[P3-T6] Native Sandbox  [P3-T12] Browser [P3-T7] Permissions
    |                       |              |
    v                       v              v
[P3-T8] MCP Client <-------+              |
    |                                     |
    v                                     v
[P3-T9] Hook System <---------------------+
    |
    v
[P3-T10] Skill System
    |
    v
[P3-T13] Quality Scoring
    |
    v
[P3-T14] OpenTelemetry

PHASE 4: UI/UX & TUI
=====================
[P4-T1] Streaming TUI <--------------------+
    |                                      |
    v                                      |
[P4-T2] Theme System                      |
    |                                      |
    v                                      v
[P4-T3] AskUserQuestion Previews     [P4-T4] Terminal Intellisense
    |                                      |
    v                                      v
[P4-T6] Dual-Model UI               [P4-T5] Slash Commands
    |                                      |
    v                                      v
[P4-T7] State Machine UI            [P4-T8] LSP Integration
    |                                      |
    v                                      v
[P4-T9] Multimodal Input            [P4-T10] 1M Context UI

PHASE 5: TESTING & QA
======================
[P5-T1] 100% Coverage
    |
    v
[P5-T2] Integration Tests
    |
    v
[P5-T3] HelixQA Challenges
    |
    v
[P5-T4] LLMsVerifier
    |
    v
[P5-T5] Security Audit
    |
    v
[P5-T6] Performance Benchmarks
    |
    v
[P5-T7] Load Testing
    |
    v
[P5-T8] Plugin Validation
    |
    v
[P5-T9] A/B Testing
    |
    v
[P5-T10] Documentation

5.2 Critical Path Identification

The critical path is the longest dependency chain that determines minimum project duration:

CRITICAL PATH (approximate duration: 76-95 days)
================================================
P0-T1 (1d) -> P0-T2 (1d) -> P0-T4 (2d) -> P0-T5 (2d)
    [Phase 0 total: 6d]
    |
    v
P1-T1 (2d) -> P1-T2 (4d) -> P1-T6 (3d)
    [Phase 1 critical: 9d]
    |
    v
P2-T1 (3d) -> P2-T2 (3d) -> P2-T6 (3d) -> P2-T7 (2d)
    [Phase 2 critical: 11d]
    |
    v
P3-T1 (3d) -> P3-T5 (4d) -> P3-T6 (3d) -> P3-T8 (5d)
    [Phase 3 critical: 15d]
    |
    v
P4-T1 (3d) -> P4-T2 (2d) -> P4-T3 (2d)
    [Phase 4 critical: 7d]
    |
    v
P5-T1 (5d) -> P5-T2 (3d) -> P5-T3 (3d) -> P5-T6 (2d) -> P5-T7 (2d)
    [Phase 5 critical: 15d]

Critical Path Total: ~63 working days (~76-95 calendar days with weekends/holidays/buffer)

5.3 Parallel Workstreams

Multiple workstreams can proceed in parallel once Phase 0 is complete:

Workstream A: LLM & Providers (Phase 1 focus) - P1-T1 -> P1-T2 -> P1-T3 -> P1-T8 - Can start immediately after P0-T5

Workstream B: Memory & Retrieval (Phase 1 focus) - P1-T4 -> P1-T5 -> P1-T7 - Can start immediately after P0-T5

Workstream C: Specification Engine (Phase 1 focus) - P1-T1 -> P1-T6 -> (feeds into Phase 3 Plan Mode) - Can start immediately after P1-T1

Workstream D: Tool Framework (Phase 2 focus) - P2-T1 -> P2-T2 -> P2-T3 - Needs P1-T2 (for LLM tool)

Workstream E: Context Management (Phase 2 focus) - P2-T4 -> P2-T5 -> P2-T8 - Needs P1-T5 (embeddings) and P1-T7 (Redis)

Workstream F: UI/UX Foundation (Phase 4 focus) - P4-T1 -> P4-T2 -> P4-T3 - Needs P2-T7 (no-flicker rendering) - Can start mid-Phase 2 once P2-T7 is complete

Workstream G: Sandboxing (Phase 3 focus) - P3-T5 -> P3-T6 - Needs P0-T3 (Containers submodule)

Workstream H: MCP Integration (Phase 3 focus) - P3-T8 - Needs P1-T2 and P2-T1

Workstream I: Quality & Testing (Phase 5 focus) - P5-T5 -> P5-T6 -> P5-T7 - Needs P3-T5 and P3-T6 complete

5.4 Merge Points (High Coordination Required)

| Merge Point | Tasks Converging | Coordination Need |
| --- | --- | --- |
| M1 (After P2-T2) | Tool suite complete | All Phase 2+ tool-dependent tasks can start |
| M2 (After P3-T1) | Plan mode ready | UI, permissions, MCP can integrate with plan mode |
| M3 (After P3-T5) | Sandboxing ready | Security audit, integration tests can begin |
| M4 (After P4-T1) | TUI streaming ready | All UI features can integrate |
| M5 (After P5-T2) | Integration tests pass | Final QA and release preparation |

Section 6: RISK REGISTER

| Risk ID | Risk Description | Probability (1-5) | Impact (1-5) | Risk Score (PxI) | Mitigation Strategy | Contingency Plan |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Circular submodule dependency causes build failures: HelixCode is a child of HelixAgent. Adding HelixAgent as a submodule of HelixCode creates a loop that git may refuse to recurse. | 4 | 5 | 20 | Add HelixAgent as shallow, non-recursive submodule with update=none config. Do NOT add to go.work. Use read-only reference pattern. | If git rejects the submodule add, maintain HelixAgent as a completely separate clone (e.g., ../HelixAgent) and reference via symlink or documentation. Do not block build on HelixAgent presence. |
| R-02 | SSH key authentication fails in CI/CD: GitHub Actions (or other CI) cannot access private repos via SSH without deployed keys. | 4 | 4 | 16 | Configure Deploy Keys or GitHub App tokens for CI. Use webfactory/ssh-agent action. Document key rotation process. | Fallback to HTTPS with Personal Access Tokens for CI. Rotate tokens via GitHub Secrets. Document token scoping (read-only). |
| R-03 | Go module version conflicts across 11 submodules: Different submodules may depend on different versions of shared libraries (e.g., Gin, Cobra, Viper, Redis client). | 4 | 4 | 16 | Centralize dependency version management in go.work. Run go work sync regularly. Pin major versions in workspace. | Use replace directives in go.work temporarily to force version alignment. Create dependency upgrade sprints after integration. |
| R-04 | LLM provider API drift breaks gateway: Provider APIs change (OpenAI, Anthropic, Google), causing runtime failures after integration. | 4 | 3 | 12 | Implement provider capability discovery and version negotiation. Abstract provider specifics behind gateway interface. Add health checks with automatic failover. | Maintain provider-specific fallback adapters. Use multiple providers for critical paths (automatic failover). Alert on provider health check failures. |
| R-05 | Context compaction loses critical semantic information: Auto-compaction may remove tokens that are essential for task completion, causing agent failure. | 3 | 4 | 12 | Multi-layer compaction strategy: first summarize, then compress, then evict by relevance. Use embedding-based relevance scoring. Preserve tool results and user directives. | Implement “pin” mechanism for critical context. Allow user to mark context as non-compactable. Fallback to manual context management mode. |
| R-06 | Sandbox escape compromises host system: Container or seccomp-bpf misconfiguration allows malicious code to escape sandbox. | 3 | 5 | 15 | Defense in depth: containers + seccomp + AppArmor/SELinux + non-root user + read-only rootfs + limited capabilities. Regular security audits. | Immediately disable sandbox execution and fall back to read-only mode. Quarantine affected sessions. Engage security team for incident response. |
| R-07 | Permission system locks out legitimate operations: Overly restrictive default permissions or wildcard misconfiguration prevents normal agent operation. | 3 | 4 | 12 | Default all permissions to ask (never deny by default). Require explicit opt-in for deny rules. Validate wildcard patterns before saving. Provide --emergency-override flag. | Emergency override flag bypasses all permission checks. Log all overrides for audit. Support gradual permission tightening after initial permissive period. |
| R-08 | 100% test coverage mandate causes schedule slip: Writing comprehensive tests for 20+ feature domains may take longer than estimated, pushing timeline. | 4 | 3 | 12 | Start test writing concurrently with feature development (TDD). Use code generation for boilerplate tests. Focus on critical path coverage first. | Allow 95% coverage as temporary gate with technical debt ticket for remaining 5%. Prioritize integration tests over unit tests for non-critical paths. |
| R-09 | Theme system has platform-specific rendering bugs: Terminal capability detection fails on exotic terminals, causing garbled output or crashes. | 3 | 2 | 6 | Extensive terminal capability matrix testing. Graceful degradation to dumb terminal mode. Platform detection with fallback chains. | UI_MODE=simple forces plain text output. Per-platform test suites in CI. Community bug reporting for unsupported terminals. |
| R-10 | MCP OAuth implementation complexity: OAuth 2.1 PKCE flow is complex, error-prone, and may not work with all MCP servers. | 3 | 3 | 9 | Use mature OAuth library (e.g., golang.org/x/oauth2). Implement comprehensive error handling. Test against reference MCP servers. | Support token-based auth as fallback for servers without OAuth. Document manual token configuration. Phase MCP OAuth as beta feature. |
| R-11 | HelixQA challenge flakiness causes false negatives: Challenge tests may fail due to non-deterministic LLM output, not actual regressions. | 4 | 3 | 12 | Implement challenge retry with exponential backoff. Use deterministic seed where possible. Grade on multiple criteria (not just exact match). Maintain challenge stability score. | Quarantine flaky challenges after 3 consecutive failures. Manual review of borderline results. Separate “stable” and “experimental” challenge suites. |
| R-12 | Performance regression under load: 100 concurrent sessions may expose memory leaks, goroutine leaks, or database connection pool exhaustion. | 3 | 4 | 12 | Load test early (not just at end). Use pprof profiling. Set resource limits and alerts. Implement circuit breakers for LLM calls. | Horizontal scaling: run multiple HelixCode instances behind load balancer. Scale PostgreSQL read replicas. Implement request queuing and backpressure. |
| R-13 | Key contributor availability: Core team members may be unavailable due to vacation, illness, or other projects. | 3 | 3 | 9 | Pair programming and knowledge sharing sessions. Document architecture decisions. Cross-train team members on critical subsystems. | Redistribute tasks based on availability. Use external contractors for well-defined, isolated tasks. Extend timeline if needed. |
| R-14 | Tree-sitter integration gaps: Context compaction relies on Tree-sitter for structural summaries. Some languages may lack parser support. | 2 | 3 | 6 | Maintain fallback to regex-based heuristics for unsupported languages. Prioritize top-10 language parsers. Use LLM-based summarization as ultimate fallback. | Document supported languages. Graceful degradation to text-level compaction. Community contribution path for new Tree-sitter parsers. |
| R-15 | Database migration conflicts: HelixMemory and HelixCode migrations may conflict on schema names, table names, or migration versioning. | 3 | 3 | 9 | Use separate PostgreSQL schemas. Centralized migration runner with ordering. Versioned migration filenames with timestamps. Pre-deployment migration test in staging. | Rename conflicting tables/columns with migration. Use schema separation (helixmemory.* vs helixcode.*). Emergency rollback via down migrations. |
| R-16 | Skill system YAML parsing vulnerabilities: Loading skills from YAML files could introduce deserialization vulnerabilities if untrusted skills are loaded. | 2 | 4 | 8 | Strict YAML schema validation. Whitelist allowed keys. Sanitize all string inputs. Load skills from trusted paths only. | Disable skill loading via --no-skills flag. Review all skill files before loading. Use static analysis on skill definitions. |
| R-17 | Embedding model compatibility: Embedding dimensions or models may change, invalidating stored vectors in pgvector. | 2 | 3 | 6 | Store embedding model version with vectors. Detect model mismatch on retrieval. Support re-embedding on model change. | Migration to re-embed all stored content. Dimension-agnostic storage if possible. Alert on model version mismatch. |
| R-18 | Subagent communication deadlock: Multiple subagents waiting on each other creates deadlock in orchestrator. | 2 | 4 | 8 | Implement timeouts on all inter-agent requests. Use directed acyclic graphs for task dependencies. Monitor for circular wait conditions. | Timeout-based cancellation of deadlocked tasks. Fallback to single-agent execution. Log deadlock patterns for post-hoc analysis. |
| R-19 | OpenTelemetry overhead impacts performance: Tracing and metrics collection adds latency to fast paths. | 2 | 2 | 4 | Use sampling (1% default, 100% on demand). Async trace export. Lightweight span creation. Benchmark with/without telemetry. | Disable telemetry via OTEL_DISABLED=1. Reduce sampling rate. Batch span export to reduce overhead. |
| R-20 | Mid-session provider switching loses context: Switching LLM providers mid-session may cause context format incompatibilities. | 3 | 3 | 9 | Normalize context format in HelixCode before sending to any provider. Abstract provider-specific message formats. Test context round-trip for each provider. | Warn user before switching. Offer to compact/summarize context on switch. Maintain per-provider context caches. |

Risk Heat Map

Impact
   5 |  R-01  R-06
   4 |  R-02  R-03  R-05  R-07  R-08  R-12
   3 |  R-04  R-10  R-11  R-15  R-18  R-20
   2 |  R-09  R-14  R-17  R-19
   1 |
     +---------------------------
       1   2   3   4   5
           Probability

HIGH RISK ZONE (PxI >= 12): R-01, R-02, R-03, R-04, R-05, R-06, R-07, R-08, R-11, R-12, R-20
MEDIUM RISK ZONE (PxI 6-11): R-09, R-10, R-13, R-14, R-15, R-16, R-17, R-18
LOW RISK ZONE (PxI < 6): R-19

APPENDIX A: Feature Inventory Summary

| Source Agent | # Features | Key Features Integrated |
| --- | --- | --- |
| Claude Code | 20 | Auto-Compaction, Permissions, Tool Persistence, Worktree Isolation, Hooks, No-Flicker Rendering, Background Tasks, Smart Editing, Plan Mode, Slash Commands, MCP Lifecycle, Skills, Session Resume, Multi-Provider Wizards, LSP, Sandboxed Shell, Themes, AskUserQuestion, Subagent Team, OpenTelemetry |
| Aider | 3 | Architect/Editor Dual-Model, 4-Layer Fuzzy Matching, Git-Native Auto-Commit |
| Cline | 3 | Plan/Act with Different Models, Shadow Git Checkpoints, Browser Automation |
| Codex | 3 | OS-Native Sandboxed Execution, Automatic Context Compaction, Stateless ZDR Architecture |
| Plandex | 3 | Cumulative Diff Review Sandbox, 2M Token Context + 20M Indexing, Version-Controlled Model Packs |
| Forge | 3 | 6 Orchestration Patterns, Quality Scoring with Gates, A/B Testing for Agent Configs |
| Kilo Code | 3 | 5 Specialized Modes + Subagent Delegation, Multi-Agent Platform State Machine, Auto Triage/Review/App Builder |
| OpenCode | 3 | 75+ Provider Support with Mid-Session Switching, LSP Integration with Diagnostics, Plugin System with 25+ Hooks |
| Gemini CLI | 3 | 1M Token Context Window, Plan Mode with ask_user, Multimodal Input |
| Amazon Q | 3 | Fig-Style Terminal Intellisense, Architecture Diagram <-> Code Sync, CDK Construct Abstraction |

Total Feature Domains: 47 distinct features across 10 source agents

APPENDIX B: Timeline Summary

| Phase | Calendar Days | Cumulative Days | Risk Level |
| --- | --- | --- | --- |
| Phase 0: Foundation | 5-7 | 5-7 | HIGH |
| Phase 1: Core Infrastructure | 14-18 | 19-25 | HIGH |
| Phase 2: CLI Agent Foundation | 18-22 | 37-47 | MEDIUM-HIGH |
| Phase 3: Power Features | 21-28 | 58-75 | HIGH |
| Phase 4: UI/UX & TUI | 14-18 | 72-93 | MEDIUM |
| Phase 5: Testing & QA | 14-18 | 86-111 | MEDIUM |

Estimated Total Duration: 86-111 calendar days (~3-4 months with 1 FTE team of 4-6 engineers)

Go-Live Target: Q2 2025 (with buffer for risk mitigation)

APPENDIX C: Team Assignment Recommendations

| Role | Responsibilities | Phases |
| --- | --- | --- |
| Integration Lead | Architecture decisions, submodule coordination, critical path management | All |
| LLM Engineer | Provider gateway, multi-model support, context compaction | 1, 2, 3 |
| Agent Engineer | Tool framework, plan mode, subagent orchestration | 2, 3 |
| Infrastructure Engineer | Sandboxing, MCP, security, build system | 0, 1, 3, 5 |
| UI/UX Engineer | TUI streaming, themes, terminal intellisense, multimodal | 4 |
| QA Engineer | Test strategy, coverage enforcement, challenge design | 5 (support throughout) |
| DevOps Engineer | CI/CD, deployment, observability, load testing | 0, 1, 5 |

End of Master Integration Plan